## Scrummaster
Scrummaster
| Sprint 1 : | William Limianto | (3 hari)
| Sprint 2 : | Johanes Novenus Demak | (3 hari)
| Sprint 3 : | Kevin Griffinsu | (3 hari)
| Sprint 4 : | Javentira Lienata | (3 hari)
| Sprint 5 : | William Limianto | (2 harI)

## Sprint 1 - Day One
Burndown Chart Sprint 1 - Day One
Sprint Backlog :
| Nama Backlog |  | Senin | Selasa | Rabu
| Penjelasan secara Umum : Apa itu Dota2? |  | 40
| Penjelasan secara Umum : Elemen pada Dota2 (Game Mode, Aktor, Item) |  | 40
| Edit Fungsionalitas dan Tampilan Bespoke |  | 40
| Role : Carry |  | 40
| Warding : Penjelasan |  | 40
| Hero Guide Sniper : Penjelasan Singkat (Tipe, Skills) |  | 60
|  | Total = | 260 | 0 | 0
Burndown Chart :
Ket : Satuan waktu dalam Menit.

## Sprint 1 - Day Two
Burndown Chart Sprint 1 - Day Two
Sprint Backlog :
| Nama Backlog |  | Senin | Selasa | Rabu
| Penjelasan secara Umum : Apa itu Dota2? |  | 40 | 0
| Penjelasan secara Umum : Elemen pada Dota2 (Game Mode, Aktor, Item) |  | 40 | 40
| Edit Fungsionalitas dan Tampilan Bespoke |  | 40 | 0
| Role : Carry |  | 40 | 40
| Warding : Penjelasan |  | 40 | 25
| Hero Guide Sniper : Penjelasan Singkat (Tipe, Skills) |  | 60 | 25
|  | Total = | 260 | 130 | 0
Burndown Chart :
Ket : Satuan waktu dalam Menit.

## Sprint 1 - Day Three
Burndown Chart Sprint 1 - Day Three
Sprint Backlog :
| Nama Backlog |  | Senin | Selasa | Rabu
| Penjelasan secara Umum : Apa itu Dota2? |  | 40 | 0 | 0
| Penjelasan secara Umum : Elemen pada Dota2 (Game Mode, Aktor, Item) |  | 40 | 40 | 0
| Edit Fungsionalitas dan Tampilan Bespoke |  | 40 | 0 | 0
| Role : Carry |  | 40 | 40 | 0
| Warding : Penjelasan |  | 40 | 25 | 0
| Hero Guide Sniper : Penjelasan Singkat (Tipe, Skills) |  | 60 | 25 | 0
|  | Total = | 260 | 130 | 0
Burndown Chart :
Ket : Satuan waktu dalam Menit.

## Sprint 2 - Day One
Burndown Chart Sprint 2 - Day ONE
Sprint Backlog :
| Nama Backlog |  | Kamis | Jumat | Sabtu
| Penjelasan Secara Umum : Game Mode Dota 2(Penjelasan , Beberapa Contoh) |  | 30
| Penjelasan Secara Umum : "Aktor " yang ada pada Dota2 (penjelasan untuk Creeps, Neutral Creeps, Tower, Ancient ,Hero) |  | 45
| Warding : Manfaat Warding |  | 65
| Role : Lane Support |  | 20
| Role : Disabler |  | 40
| Guide Sniper : Item Build (Early , Mid , Late) |  | 65
|  | Total = | 265 | 0 | 0
Burndown Chart :
Ket : Satuan waktu dalam Menit.

## Sprint 2 - Day Two
Burndown Chart Sprint 2 - Day Two

## Sprint 2 - Day Three
Burndown Chart Sprint 2 - Day Three

## Sprint 3 - Day One
Burndown Chart Sprint 3 - Day One

## Sprint 3 - Day Two
Burndown Chart Sprint 3 - Day Two

## Sprint 3 - Day Three
Burndown Chart Sprint 3 - Day Three

## Sprint 4 - Day One
Burndown Chart Sprint 4 - Day One

## Sprint 4 - Day Two
Burndown Chart Sprint 4 - Day Two

## Sprint 4 - Day Three
Burndown Chart Sprint 4 - Day Three

## Sprint 5 - Day One
Burndown Chart Sprint 5 - Day One

## Sprint 5 - Day Two
Burndown Chart Sprint 5 - Day Two